## ClientBlockerFuerHeatmap
is_idle_time | WorkOrIdleTime | should_have_escalated | Category | Explanation | Duration | Original entry | Color
FALSE | work | short | Meetings | Team Retro | 1 | 0.041667
FALSE | work | short | Meetings | Team Retro | 2 | 0.083333
FALSE | work | short | Supervision Work | Analysis of unexpected outcomes | 1.5 | 0.0625
FALSE | work | short | Rework | Fixing the wiget25 bug after QA | 9 | 9:00
FALSE | work | short | Rework | Collect additional data for business stakeholders | 14 | 0.58333
FALSE | work | short | Rework | Evaluate additional solutions | 16 | 0.66667
FALSE | work | short | Rework | Create testcase that should have been done in analysis | 1.5 | 1:30
FALSE | work | short | Unexpected Rework | Re-negotiated agreement with support team | 2.5 | 2:30
FALSE | work | short | Unexpected Rework | Discovered Additional processes for the test plan | 10 | 10:00
FALSE | work | short | Unexpected Rework | Evaluate new solution strategy from business owner | 26 | 26:00
FALSE | work | short | Unexpected Rework | Found Unclear Workflow Logic; Rework | 38 | 1899-12-31 14:00
FALSE | work | short | Unexpected Rework | Really understand business process | 12 | 12:00
FALSE | work | short | Unexpected Rework | Research "Lunar Landing Module" SOPs | 31.5 | 1899-12-31 07:30
FALSE | work | short | Unexpected Rework | Checking test for unexpected behaviour | 16 | 0.66667
TRUE | idle | short | Meetings | Interaction with HR-department | 1.75 | 1:45
TRUE | idle | short | Meetings | Support outside assigned mission | 1.5 | 0.0625
TRUE | idle | short | Wait for external | Process information required to create test plan missing | 0.75 | 0:45
TRUE | idle | short | Wait for internal | Waiting for approval of acceptance criteria by feature owners | 1.5 | 0.0625
TRUE | idle | short | Wait for internal | Waiting for approval of acceptance criteria by feature owners | 1 | 0.041667
TRUE | idle | short | Wait for internal | Waiting for Code Review to start | 1.5 | 1:30
TRUE | idle | short | Wait for internal | Waiting for stakeholder to cralify problem | 0.5 | 0:30
TRUE | idle | short | Wait for internal | Waiting for PR approval | 2 | 2:00
TRUE | idle | Too long | Deployment | Pipeline not Working | 2.5 | 0.10417
TRUE | idle | Too long | Deployment | Waiting for Deployment | 6 | 0.25
TRUE | idle | Too long | Deployment | Waiting for Deployment | 16 | 16:00
TRUE | idle | Too long | Deployment | Waiting for Deployment | 8 | 8:00
TRUE | idle | Too long | Capacity exausted | Work on widget25 has stop to work on widget36 | 21.5 | 21:30
TRUE | idle | Too long | Capacity exausted | Work on widget36 has stop to work on widget42 | 15 | 15:00
TRUE | idle | Too long | Policy Agreements | Reviewers not Available | 7 | 0.29167
TRUE | idle | Too long | Unplanned Work | Buildpipeline unreliable | 4 | 4:00
TRUE | idle | Too long | Unplanned Work | Cross-Department Database-Support | 8 | 0.33333
TRUE | idle | Too long | Unplanned Work | Supporting facilities management (power outage) | 5.5 | 5:30
TRUE | idle | Too long | Unplanned Work | Quality checks | 4 | 0.16667
TRUE | idle | Too long | Unplanned Work | Fix plumbing (database engine) | 3 | 0.125
TRUE | idle | Too long | Unplanned Work | handover due to personell issues | 56 | 1900-01-01 08:00
TRUE | idle | Too long | Unplanned Work | Onboarding | 25 | 1899-12-31 01:00
TRUE | idle | Too long | Unplanned Work | Education of new team members | 24 | 24:00
TRUE | idle | Too long | Wait for external | Acceptance test verification | 13 | 13:00
TRUE | idle | Too long | Wait for external | Gather background information | 12 | 12:00
TRUE | idle | Too long | Wait for external | Waiting for Stakeholder | 5.75 | 0.23958
TRUE | idle | Too long | Wait for external | Waiting for supplier | 6.5 | 6:30
TRUE | idle | Too long | Wait for external | Waiting for contractor | 3 | 3:00
TRUE | idle | Too long | Wait for internal | Waiting for all people to be available | 7.4167 | 7:25
TRUE | idle | Too long | Wait for internal | Waiting for all people to be available | 2.5 | 0.10417
TRUE | idle | Too long | Wait for internal | Waiting for all people to be available | 7.25 | 0.30208
TRUE | idle | Too long | Wait for internal | Waiting for all people to be available | 5 | 0.20833